## Sheet1
Date / Time | Length in minutes | Task | Activity | Result | Responsibility | Remarks
2019-01-15 | 120 | Installing MongoDB Connector for PHP |  | Working connection between PHP and MongoDB | Yasin Ergüven
2019-01-15 | 60 | Starting with Migration in Java |  | Not finished with Migration | Yasin Ergüven
2019-01-16 | 100 | Finishing Migration for MongoDB |  | Working Migration of data in MongoDB | Yasin Ergüven
2019-01-18 | 100 | Starting with Employee Administration Use Case MongoDB Implementation |  | Connection between mongoDB database and php works | Yasin Ergüven
2019-01-20 | 100 | Adding and Deletion implementation for Employee Administration |  | Working add and delete | Yasin Ergüven
2019-01-21 | 150 | Update Implementation |  | Working update for Employee Administration | Yasin Ergüven
2019-01-22 | 120 | Starting with Hall Administration Use Case MongoDB implementation |  | Connectino to halls table in mongoDB database works | Yasin Ergüven
2019-01-23 | 120 | Implementing CRUD operations for hall administration |  | Working add, delete & update for halls | Yasin Ergüven
2019-01-24 | 100 | Fixing bugs and finishing use case "Hall Administration" |  | Existing bugs eleminated | Yasin Ergüven
2019-01-26 | 300 | Group meeting, discussion and implementation, searching & fixing bugs for halls & employees |  | Existing bugs eleminated | Group
2019-01-27 | 150 | Finishing Use Cases, testing of all use cases |  | Tested functionalites of the usecases | Yasin Ergüven
2019-01-28 | 60 | Minor fixes and changes, finishing project |  | Finished project | Yasin Ergüven