## Sheet1
Date / Time | Length in minutes | Task | Activity | Result | Responsibility | Remarks
13.12.2018 | 150 | Group discussion & MySQL & GIT setup |  | Decisions which frameworks to use and use case distribution | Group | First project assessment
18.12.2018 | 70 | Setup of apache / Xampp |  | Making sure everything worked on both my work PCs | Oliver Schweiger
18.12.2018 | 25 | Create table and Drop scripts |  | Tables are now created and dropped correctly with all necessary attributes | Oliver Schweiger | keep in mind the order when creating & dropping
18.12.2018 | 60 | Learning how to use the mysqli connector in PHP |  | Connection to database now working | Oliver Schweiger | use mysqli rather than mysql
18.12.2018 | 150 | Start of php implementation of Use Case III: view films |  | Inserted films are now shown in html, search for title function | Oliver Schweiger
19.12.2018 | 70 | Creation of links within Use Case III |  | Added links that show screenings for films & film details for screenings | Oliver Schweiger
19.12.2018 | 150 | Continuation of php implementation of Use Case VI: manage films |  | Delete now works on button press | Oliver Schweiger | to-do: place button next to tuple
19.12.2018 | 70 | Continuation of php implementation of Use Case VI: manage films |  | Update button that links to update-page (still buggy) | Oliver Schweiger
20.12.2018 | 140 | Working on insert for Use Case VI |  | Insert over web page now working | Oliver Schweiger
20.12.2018 | 120 | Continued work on Update functionality |  | Fixed update button, update page now working with pre sed values in form | Oliver Schweiger | placed delete & update button next to tuple now
21.12.2018 | 120 | Started on Use Case VII: manage screenings |  | Creating links, insert, delete and update functionality | Oliver Schweiger | Could copy some parts from my other usecase, since they are similar
31.12.2018 | 180 | Team discussion over internet |  | Summary of work done so far, define to-dos | Group
4.1.2019 | 60 | Changed film tuple to contain the duration (removed it from screening) |  | Fixed all php contents to reflect that change | Oliver Schweiger | updates were needed in 6 php files
5.1.2019 | 180 | Fixes & additional functions concerning DateTime in Use Case VII |  | User can now look for current screenings (today, tomorrow, this week) | Oliver Schweiger | using mysql CURRTIME instead of PHP timezones now
5.1.2019 | 30 | Sort tables by date in Use Case VII |  | Screenings are now sorted by date | Oliver Schweiger | added ORDER BY to $sql variable
6.1.2019 | 30 | Worked on NoSQL slides |  | Added an example | Oliver Schweiger | idea: screenings nested inside film
6.1.2019 | 120 | Team discussion |  | Finalization talks about MS2 | Group
6.1.2019 | 60 | Fixing bugs & small changes to Use Cases III, VI and VII |  | Bugs regarding reload of page after insert | Oliver Schweiger | Maybe change to POST later