## Sheet1
Date / Time | Length in minutes | Task | Activity | Result | Responsibility | Remarks
13.12.2018 | 150 | Group discussion & MySQL & GIT setup |  | Decisions which frameworks to use and use case distribution | Group | First project assignment
2018-12-20 | 60 | Installation & set up of XAMPP |  | Have access to the functionality of XAMPP | Yasin Ergüven
2018-12-20 | 100 | Starting with use case "Employee Administration" implementation |  | Basic structure of the webpage was built | Yasin Ergüven
2018-12-23 | 100 | Continuing with implementation of the use case "Employee Administration" |  | View of the employee administration finished | Yasin Ergüven
2018-12-23 | 50 | Ensuring that database connection works properly |  | Database connection works via mysqli connector in PHP | Yasin Ergüven
2018-12-26 | 150 | Adding CRUD operations for employee administration |  | Functionality for adding, deleting, updating and reading provided | Yasin Ergüven
2018-12-27 | 120 | Fixing bugs and errors regarding crud operations for use case |  | CRUD operations work now in a proper way | Yasin Ergüven
2018-12-28 | 150 | Starting with use case Hall Administration" implementation |  | Basic structure of the webpage was built | Yasin Ergüven
2018-12-29 | 100 | Adding CRUD operations for hall administration |  | Functionality for adding, deleting, updating and reading provided | Yasin Ergüven
31.12.2018 | 120 | Team discussion over internet |  | Summary of work done so far, define to-dos | Group
2019-01-03 | 130 | Fixing bugs and finishing use case "Hall Administration" |  | Hall administration works properly without bugs | Yasin Ergüven
2019-01-04 | 120 | Use Case "Employee Administration": Show subordinates functionality |  | Admin can now see manager relationship between employees | Yasin Ergüven
2019-01-05 | 180 | Realization of the unary relationship inside employees |  | Admin can now see the manager of employees (and vice versa) more in detail | Yasin Ergüven
2019-01-06 | 60 | Testing and finding/removing bugs regarding the two use cases |  | Existing bugs eleminated | Yasin Ergüven
2019-01-06 | 120 | Team discussion |  | Finalization talks about MS2 | Group