## Tabelle1
Date / Time | Length in minutes | Task | Activity | Result | Responsibility | Remarks
13.12.2018 | 150 | Group discussion & MySQL & GIT setup |  | Decisions which frameworks to use and use case distribution | Group | First project assessment
18.12.2018 | 180 | Created skeleton of the homepage |  | The user can now access the homepage and klick through the buttons | Alexander Ramharter
2018-12-20 | 120 | Implemented Sign in (USE CASE II) |  | Employee can now sign in and he stays logged in using global php session variables | Alexander Ramharter
2018-12-21 | 120 | Changed Sign in (USE CASE II) |  | Customer can now login | Alexander Ramharter
2018-12-23 | 180 | Changed Sign in and implemented Register (USE CASE II & I) |  | Admin can sign in using specific credentials; users can register - they get inserted into the customer table | Alexander Ramharter
2018-12-29 | 120 | Implemented role based access control (USE CASE XI) |  | employee has access to update, delete, insert. Customer can klick buy tickets | Alexander Ramharter
31.12.2018 | 180 | Team discussion over internet |  | Summary of work done so far, define to-dos | Group
2019-01-02 | 120 | Design change - new button for loggedin user (USE CASE X) |  | Made the theme brighter and added screening button as well as button for user | Alexander Ramharter
2019-01-03 | 120 | Bug fixes and design changes |  | A view in the database was deleted, register got an exit button | Alexander Ramharter
2019-01-04 | 60 | Role based access bugfixes (USE CASE XI) |  | Admin sees now the update and delete functions for hall, employee | Alexander Ramharter
2019-01-04 | 90 | "Delete Account" Button |  | Customer can delete his account | Alexander Ramharter
2019-01-04 | 60 | Several bugfixes |  | ID now always gets saved | Group
2019-01-05 | 60 | Role based access bugfixes (USE CASE XI) |  | ID's now only get shown to employee | Alexander Ramharter
2019-01-06 | 120 | Team discussion |  | Finalization talks about MS2 | Group
2019-01-07 | 120 | Implemented user's password change (USE CASE X) |  | User can now change his password | Alexander Ramharter