## Sheet1
Date | Length in minutes | Task | Activity | Result | Responsibility | Remarks
2019-01-15 | 220 | Java tool, General | Updated project structure, added Maven support, installed MongoDB, wrote connector and main classes. | Working MS2 project, functioning MongoDB instance | Team
2019-01-21 | 30 | Java tool | Successfully connected to MongoDB instance on localhost, added mainWindow frame + buttons. | Working connection and GUI (start windows + main window) | Team
2019-01-21 | 30 | Java tool | Finished film entry class and finalized project structure for MS3. | Film Entry working, more fluid UIX | Team
2019-01-22 | 150 | Java tool | Implemented ScreeningEntry, CustomerEntry, TicketEntry, HallEntry, SeatEntry, EmployeeEntry & ManagerEntry. | Manual data entry complete | Team
2019-01-23 | 20 | Java tool | Fixed naming conventions and inserts in SQLMigrator. | Improved SQLMigrator | Team
2019-01-26 | 150 | Java tool | Tried mapping our mongoDB infrastructure to REST using the Spring Boot API. | Failed, reverted to previous state on git | Team, Utz Nisslmüller
2019-01-26 | 135 | Web / PHP | Set up infrastructure and started transforming SQL statements into mongo queries. | Working PHP mongo connector + ticket output. | Utz Nisslmüller
2019-01-26 | 210 | Web / PHP | Tried several approaches for making multiple nested queries, and failed | Better overview of specific problems which are still present. | Utz Nisslmüller
2019-01-27 | 330 | Web / PHP | Implemented complete ticket functionality with new PHP driver for Mongo | Ticket CRUD operations complete. | Utz Nisslmüller
2019-01-27 | 120 | Java tool | General bugfixing, added stats and progress bars. | Final client | Team
2019-01-28 | 120 | General, SQL | Created smaller SQL scripts for the presentation on Tuesday. Integrated them into our Java tool | Bug free MS2 implementation, complete SQL scripts. | Team
TOTAL
Team | 840
Myself | 825